## example
ID | Title | Description | Dependencies | Started | Finished | Low | Estimate | High
a | Cut fur | Cut fur to the shape of the needed bear. |  | 2020-01-01 | 2020-01-03 | 1 | 2 | 4
b | Stuff fur | Stuff the cut fur to the right density for the quality of the product. | a | 2020-01-03 | 2020-01-14 | 4 | 6 | 13
c | Cut cloth | Cut cloth for the bear‚Äôs size |  | 2020-01-14 |  | 1 | 2 | 4
d | Sew clothes | Sew cloth into bear clothing | c |  |  | 1 | 2 | 6
e | Embroider | Embroider custom name and message on the bear | d |  |  | 2 | 2 | 2
f | Cut accessories | Cut ordered bear accessories |  |  |  | 0 | 1 | 3
g | Sew accessories | Attach accessories to the bear | f |  |  | 0 | 2 | 3
h | Dress bear | Dress bear in custom clothing | b, e, g |  |  | 3 | 3 | 3
i | Package bear | Package bear for stackable shipping | h |  |  | 1 | 1 | 1
j | Ship bear | Transport bear to shipping | i, e |  |  | 1 | 1 | 1